## ITO Records
Sequence | Process Group | Knowledge Area | Process | Type | Name | Details
1 | Initiating | Project Integration Management | Develop Project Charter | I | Agreements
2 | Initiating | Project Integration Management | Develop Project Charter | I | Business documents | Business case
3 | Initiating | Project Integration Management | Develop Project Charter | I | Enterprise environmental factors
4 | Initiating | Project Integration Management | Develop Project Charter | I | Organizational process assets
5 | Initiating | Project Integration Management | Develop Project Charter | T | Expert judgment
6 | Initiating | Project Integration Management | Develop Project Charter | T | Data gathering | Brainstorming; Focus groups; Interviews
7 | Initiating | Project Integration Management | Develop Project Charter | T | Interpersonal & team skills | Conflict management; Facilitation; Meeting management
8 | Initiating | Project Integration Management | Develop Project Charter | T | Meetings
9 | Initiating | Project Integration Management | Develop Project Charter | O | Project charter
10 | Initiating | Project Integration Management | Develop Project Charter | O | Assumption log
11 | Planning | Project Integration Management | Develop Project Management Plan | I | Outputs from other processes
12 | Planning | Project Integration Management | Develop Project Management Plan | I | Project charter
13 | Planning | Project Integration Management | Develop Project Management Plan | I | Enterprise environmental factors
14 | Planning | Project Integration Management | Develop Project Management Plan | I | Organizational process assets
15 | Planning | Project Integration Management | Develop Project Management Plan | T | Expert judgment
16 | Planning | Project Integration Management | Develop Project Management Plan | T | Data gathering | Brainstorming; Checklists; Focus groups; Interviews
17 | Planning | Project Integration Management | Develop Project Management Plan | T | Interpersonal & team skills | Conflict management; Facilitation; Meeting management
18 | Planning | Project Integration Management | Develop Project Management Plan | T | Meetings
19 | Planning | Project Integration Management | Develop Project Management Plan | O | Project management plan | Change management plan; Configuration management plan; Performance measurement baseline; Project life cycle; Development approach; Management reviews
20 | Executing | Project Integration Management | Direct and Manage Project Work | I | Project management plan | Any component
21 | Executing | Project Integration Management | Direct and Manage Project Work | I | Project documents | Change log; Lessons learned register; Milestone list; Project communications; Project schedule; Requirements traceability matrix; Risk register; Risk report
22 | Executing | Project Integration Management | Direct and Manage Project Work | I | Approved change requests
23 | Executing | Project Integration Management | Direct and Manage Project Work | I | Enterprise environmental factors
24 | Executing | Project Integration Management | Direct and Manage Project Work | I | Organizational process assets
25 | Executing | Project Integration Management | Direct and Manage Project Work | T | Expert judgment
26 | Executing | Project Integration Management | Direct and Manage Project Work | T | Project Management Information System (PMIS)
27 | Executing | Project Integration Management | Direct and Manage Project Work | T | Meetings
28 | Executing | Project Integration Management | Direct and Manage Project Work | O | Deliverables
29 | Executing | Project Integration Management | Direct and Manage Project Work | O | Work Performance Data
30 | Executing | Project Integration Management | Direct and Manage Project Work | O | Issue Log
31 | Executing | Project Integration Management | Direct and Manage Project Work | O | Change requests
32 | Executing | Project Integration Management | Direct and Manage Project Work | O | Project management plan updates | Any component
33 | Executing | Project Integration Management | Direct and Manage Project Work | O | Project documents updates | Activity list; Assumption log; Lessons learned register; Requirements documentation; Risk register; Stakeholder register
34 | Executing | Project Integration Management | Direct and Manage Project Work | O | Organizational process assets updates
35 | Executing | Project Integration Management | Manage Project Knowledge | I | Project management plan | Any component
36 | Executing | Project Integration Management | Manage Project Knowledge | I | Project documents
37 | Executing | Project Integration Management | Manage Project Knowledge | I | Deliverables
38 | Executing | Project Integration Management | Manage Project Knowledge | I | Enterprise environmental factors
39 | Executing | Project Integration Management | Manage Project Knowledge | I | Organizational process assets
40 | Executing | Project Integration Management | Manage Project Knowledge | T | Expert judgment
41 | Executing | Project Integration Management | Manage Project Knowledge | T | Knowledge management
42 | Executing | Project Integration Management | Manage Project Knowledge | T | Information management
43 | Executing | Project Integration Management | Manage Project Knowledge | T | Interpersonal & team skills | Active listening; Facilitation; Leadership; Networking; Political awareness
44 | Executing | Project Integration Management | Manage Project Knowledge | O | Lessons learned Register
45 | Executing | Project Integration Management | Manage Project Knowledge | O | Project management plan updates | Any component
46 | Executing | Project Integration Management | Manage Project Knowledge | O | Organizational process assets updates
47 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | I | Project management plan | Any component
48 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | I | Project documents | Assumption log; Basis of estimates; Cost forecasts; Issue log; Lessons learned register; Milestone list; Quality reports; Risk register; Risk report; Schedule forecasts
49 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | I | Work performance Information
50 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | I | Agreements
51 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | I | Enterprise environmental factors
52 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | I | Organizational process assets
53 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | T | Expert judgment
54 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | T | Data analysis | Alternatives analysis; Cost-benefit analysis; Earned value analysis; Root cause analysis; Trend analysis; Variance analysis
55 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | T | Decision making | Voting
56 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | T | Meetings
57 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | O | Work performance Reports
58 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | O | Change requests
59 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | O | Project management plan updates | Any component
60 | Monitoring & Controlling | Project Integration Management | Monitor and Control Project Work | O | Project documents updates | Cost forecasts; Issue log; Lessons learned register; Risk register; Schedule forecasts
61 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | I | Project management plan | Change management plan; Configuration management plan; Scope baseline; Schedule baseline; Cost baseline
62 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | I | Project documents | Basis of estimates; Change log; Requirements traceability matrix; Risk report
63 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | I | Work performance Reports
64 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | I | Change requests
65 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | I | Enterprise environmental factors
66 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | I | Organizational process assets
67 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | T | Expert judgment
68 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | T | Change control tools
69 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | T | Data analysis
70 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | T | Decision making
71 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | T | Meetings
72 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | O | Approved change requests
73 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | O | Project management plan updates | Any component
74 | Monitoring & Controlling | Project Integration Management | Perform Integrated Change Control | O | Project documents updates | Change log
75 | Closing | Project Integration Management | Close Project or Phase | I | Project charter
76 | Closing | Project Integration Management | Close Project or Phase | I | Project management plan | All components
77 | Closing | Project Integration Management | Close Project or Phase | I | Project documents | Assumption log; Basis of estimates; Change log; Issue log; Lessons learned register; Milestone list; Project communications; Quality control measurements; Quality reports; Requirements documentation; Risk register; Risk report
78 | Closing | Project Integration Management | Close Project or Phase | I | Accepted deliverables
79 | Closing | Project Integration Management | Close Project or Phase | I | Business documents | Business case; Benefits management plan
80 | Closing | Project Integration Management | Close Project or Phase | I | Agreements
81 | Closing | Project Integration Management | Close Project or Phase | I | Procurement documentation | Bid Documents; Procurement statement of work; Independent cost estimates; Source selection criteria
82 | Closing | Project Integration Management | Close Project or Phase | I | Organizational process assets
83 | Closing | Project Integration Management | Close Project or Phase | T | Expert judgment
84 | Closing | Project Integration Management | Close Project or Phase | T | Data analysis | Document analysis; Regression analysis; Trend analysis; Variance analysis
85 | Closing | Project Integration Management | Close Project or Phase | T | Meetings
86 | Closing | Project Integration Management | Close Project or Phase | O | Project documents updates | Lessons learned register
87 | Closing | Project Integration Management | Close Project or Phase | O | Final product, service, or result transition
88 | Closing | Project Integration Management | Close Project or Phase | O | Final report
89 | Closing | Project Integration Management | Close Project or Phase | O | Organizational process assets updates
90 | Planning | Project Scope Management | Plan Scope Management | I | Project charter
91 | Planning | Project Scope Management | Plan Scope Management | I | Project management plan | Quality management plan; Project life cycle; Development approach
92 | Planning | Project Scope Management | Plan Scope Management | I | Enterprise environmental factors
93 | Planning | Project Scope Management | Plan Scope Management | I | Organizational process assets
94 | Planning | Project Scope Management | Plan Scope Management | T | Expert judgment
95 | Planning | Project Scope Management | Plan Scope Management | T | Data analysis | Alternatives analysis
96 | Planning | Project Scope Management | Plan Scope Management | T | Meetings
97 | Planning | Project Scope Management | Plan Scope Management | O | Scope management plan
98 | Planning | Project Scope Management | Plan Scope Management | O | Requirements management plan
99 | Planning | Project Scope Management | Collect Requirements | I | Project charter
100 | Planning | Project Scope Management | Collect Requirements | I | Project management plan | Scope management plan; Requirements management plan; Stakeholder engagement plan
101 | Planning | Project Scope Management | Collect Requirements | I | Project documents | Assumption log; Lessons learned register; Stakeholder register
102 | Planning | Project Scope Management | Collect Requirements | I | Business documents | Business case
103 | Planning | Project Scope Management | Collect Requirements | I | Agreements
104 | Planning | Project Scope Management | Collect Requirements | I | Enterprise environmental factors
105 | Planning | Project Scope Management | Collect Requirements | I | Organizational process assets
106 | Planning | Project Scope Management | Collect Requirements | T | Expert judgment
107 | Planning | Project Scope Management | Collect Requirements | T | Data gathering | Brainstorming; Interviews; Focus groups; Questionnaires & surveys; Benchmarking
108 | Planning | Project Scope Management | Collect Requirements | T | Data analysis | Document analysis
109 | Planning | Project Scope Management | Collect Requirements | T | Decision making | Voting; Autocratic decision making; Multi-criteria decision analysis
110 | Planning | Project Scope Management | Collect Requirements | T | Data representation | Affinity diagrams; Mind mapping
111 | Planning | Project Scope Management | Collect Requirements | T | Interpersonal & team skills | Nominal group technique; Observation/conversation; Facilitation
112 | Planning | Project Scope Management | Collect Requirements | T | Context diagram
113 | Planning | Project Scope Management | Collect Requirements | T | Prototypes
114 | Planning | Project Scope Management | Collect Requirements | O | Requirements documentation
115 | Planning | Project Scope Management | Collect Requirements | O | Requirements traceability matrix
116 | Planning | Project Scope Management | Define Scope | I | Project charter
117 | Planning | Project Scope Management | Define Scope | I | Project management plan | Scope management plan
118 | Planning | Project Scope Management | Define Scope | I | Project documents | Assumption log; Requirements documentation; Risk register
119 | Planning | Project Scope Management | Define Scope | I | Enterprise environmental factors
120 | Planning | Project Scope Management | Define Scope | I | Organizational process assets
121 | Planning | Project Scope Management | Define Scope | T | Expert judgment
122 | Planning | Project Scope Management | Define Scope | T | Data analysis | Alternatives analysis
123 | Planning | Project Scope Management | Define Scope | T | Decision making | Multi-criteria decision analysis
124 | Planning | Project Scope Management | Define Scope | T | Interpersonal & team skills | Facilitation
125 | Planning | Project Scope Management | Define Scope | T | Product analysis
126 | Planning | Project Scope Management | Define Scope | O | Project scope statement
127 | Planning | Project Scope Management | Define Scope | O | Project documents updates | Assumption log; Requirements documentation; Requirements traceability matrix; Stakeholder register
128 | Planning | Project Scope Management | Create WBS | I | Project management plan | Scope management plan
129 | Planning | Project Scope Management | Create WBS | I | Project documents | Project scope statement; Requirements documentation
130 | Planning | Project Scope Management | Create WBS | I | Enterprise environmental factors
131 | Planning | Project Scope Management | Create WBS | I | Organizational process assets
132 | Planning | Project Scope Management | Create WBS | T | Expert judgment
133 | Planning | Project Scope Management | Create WBS | T | Decomposition
134 | Planning | Project Scope Management | Create WBS | O | Scope baseline
135 | Planning | Project Scope Management | Create WBS | O | Project documents updates | Assumption log; Requirements documentation
136 | Monitoring & Controlling | Project Scope Management | Validate Scope | I | Project management plan | Scope management plan; Requirements management plan; Scope baseline
137 | Monitoring & Controlling | Project Scope Management | Validate Scope | I | Project documents | Lessons learned register; Quality reports; Requirements documentation; Requirements traceability matrix
138 | Monitoring & Controlling | Project Scope Management | Validate Scope | I | Verified deliverables
139 | Monitoring & Controlling | Project Scope Management | Validate Scope | I | Work performance data
140 | Monitoring & Controlling | Project Scope Management | Validate Scope | T | Inspection
141 | Monitoring & Controlling | Project Scope Management | Validate Scope | T | Decision making | Voting
142 | Monitoring & Controlling | Project Scope Management | Validate Scope | O | Accepted deliverables
143 | Monitoring & Controlling | Project Scope Management | Validate Scope | O | Work performance Information
144 | Monitoring & Controlling | Project Scope Management | Validate Scope | O | Change requests
145 | Monitoring & Controlling | Project Scope Management | Validate Scope | O | Project documents updates | Lessons learned register; Requirements documentation; requirements traceability matrix
146 | Monitoring & Controlling | Project Scope Management | Control Scope | I | Project management plan | Scope management plan; Requirements management plan; Change management plan; Configuration management plan; Scope baseline; Performance measurement baseline
147 | Monitoring & Controlling | Project Scope Management | Control Scope | I | Project documents | Lessons learned register; Requirements documentation; Requirements traceability matrix
148 | Monitoring & Controlling | Project Scope Management | Control Scope | I | Work performance data
149 | Monitoring & Controlling | Project Scope Management | Control Scope | I | Organizational process assets
150 | Monitoring & Controlling | Project Scope Management | Control Scope | T | Data analysis | Variance analysis; Trend analysis
151 | Monitoring & Controlling | Project Scope Management | Control Scope | O | Work performance Information
152 | Monitoring & Controlling | Project Scope Management | Control Scope | O | Change requests
153 | Monitoring & Controlling | Project Scope Management | Control Scope | O | Project management plan updates | Scope management plan; Scope baseline; Schedule baseline; Cost baseline; Performance measurement baseline
154 | Monitoring & Controlling | Project Scope Management | Control Scope | O | Project documents updates | Lessons learned register; Requirements documentation; requirements traceability matrix
155 | Planning | Project Schedule Management | Plan Schedule Management | I | Project charter
156 | Planning | Project Schedule Management | Plan Schedule Management | I | Project management plan | Scope management plan; Development approach
157 | Planning | Project Schedule Management | Plan Schedule Management | I | Enterprise environmental factors
158 | Planning | Project Schedule Management | Plan Schedule Management | I | Organizational process assets
159 | Planning | Project Schedule Management | Plan Schedule Management | T | Expert judgment
160 | Planning | Project Schedule Management | Plan Schedule Management | T | Data analysis | Alternatives analysis
161 | Planning | Project Schedule Management | Plan Schedule Management | T | Meetings
162 | Planning | Project Schedule Management | Plan Schedule Management | O | Schedule management plan
163 | Planning | Project Schedule Management | Define Activities | I | Project Management plan | Schedule management plan; Scope baseline
164 | Planning | Project Schedule Management | Define Activities | I | Enterprise environmental factors
165 | Planning | Project Schedule Management | Define Activities | I | Organizational process assets
166 | Planning | Project Schedule Management | Define Activities | T | Expert judgment
167 | Planning | Project Schedule Management | Define Activities | T | Decomposition
168 | Planning | Project Schedule Management | Define Activities | T | Rolling wave planning
169 | Planning | Project Schedule Management | Define Activities | T | Meetings
170 | Planning | Project Schedule Management | Define Activities | O | Activity list
171 | Planning | Project Schedule Management | Define Activities | O | Activity attributes
172 | Planning | Project Schedule Management | Define Activities | O | Milestone list
173 | Planning | Project Schedule Management | Define Activities | O | Change requests
174 | Planning | Project Schedule Management | Define Activities | O | Project management plan updates | Schedule baseline; Cost baseline
175 | Planning | Project Schedule Management | Sequence Activities | I | Project management plan | Schedule management plan; Scope baseline
176 | Planning | Project Schedule Management | Sequence Activities | I | Project documents | Activity attributes; Activity list; Assumption log; Milestone list
177 | Planning | Project Schedule Management | Sequence Activities | I | Enterprise environmental factors
178 | Planning | Project Schedule Management | Sequence Activities | I | Organizational process assets
179 | Planning | Project Schedule Management | Sequence Activities | T | Precedence diagramming method
180 | Planning | Project Schedule Management | Sequence Activities | T | Dependency determination and integration
181 | Planning | Project Schedule Management | Sequence Activities | T | Leads and lags
182 | Planning | Project Schedule Management | Sequence Activities | T | Project Management Information System (PMIS)
183 | Planning | Project Schedule Management | Sequence Activities | O | Project schedule network diagrams
184 | Planning | Project Schedule Management | Sequence Activities | O | Project documents updates | Activity attributes; Activity list; Assumption log; Milestone list
185 | Planning | Project Schedule Management | Estimate Activity Durations | I | Project management plan | Schedule management plan; Scope baseline
186 | Planning | Project Schedule Management | Estimate Activity Durations | I | Project documents | Activity Attributes; Activity list; Assumption log; Lessons learned register; Milestone list; Project team assignments; Resource breakdown structure; Resource calendars; Resource requirements; Risk register
187 | Planning | Project Schedule Management | Estimate Activity Durations | I | Enterprise environmental factors
188 | Planning | Project Schedule Management | Estimate Activity Durations | I | Organizational process assets
189 | Planning | Project Schedule Management | Estimate Activity Durations | T | Expert judgment
190 | Planning | Project Schedule Management | Estimate Activity Durations | T | Analogous estimating
191 | Planning | Project Schedule Management | Estimate Activity Durations | T | Parametric estimating
192 | Planning | Project Schedule Management | Estimate Activity Durations | T | Three-point estimating
193 | Planning | Project Schedule Management | Estimate Activity Durations | T | Bottom-up estimating
194 | Planning | Project Schedule Management | Estimate Activity Durations | T | Data analysis | Alternatives analysis; Reserve analysis
195 | Planning | Project Schedule Management | Estimate Activity Durations | T | Decision making | Voting
196 | Planning | Project Schedule Management | Estimate Activity Durations | T | Meetings
197 | Planning | Project Schedule Management | Estimate Activity Durations | O | Duration of estimates
198 | Planning | Project Schedule Management | Estimate Activity Durations | O | Basis of estimates
199 | Planning | Project Schedule Management | Estimate Activity Durations | O | Project documents updates | Activity attributes; Assumption log; Lessons learned register
200 | Planning | Project Schedule Management | Develop Schedule | I | Project management plan | Schedule management plan; Scope baseline
201 | Planning | Project Schedule Management | Develop Schedule | I | Project documents | Activity attributes; Activity list; Basis of estimates; Duration of estimates; Lessons learned register; Milestone list; Project schedule network diagrams; Project team assignments; Resource calendars; Resource requirements; Risk register
202 | Planning | Project Schedule Management | Develop Schedule | I | Agreements
203 | Planning | Project Schedule Management | Develop Schedule | I | Enterprise environmental factors
204 | Planning | Project Schedule Management | Develop Schedule | I | Organizational process assets
205 | Planning | Project Schedule Management | Develop Schedule | T | Schedule network analysis
206 | Planning | Project Schedule Management | Develop Schedule | T | Critical path method
207 | Planning | Project Schedule Management | Develop Schedule | T | Resource optimization
208 | Planning | Project Schedule Management | Develop Schedule | T | Data analysis | What-if scenario analysis; Simulation
209 | Planning | Project Schedule Management | Develop Schedule | T | Leads and lags
210 | Planning | Project Schedule Management | Develop Schedule | T | Schedule compression
211 | Planning | Project Schedule Management | Develop Schedule | T | Project Management Information System (PMIS)
212 | Planning | Project Schedule Management | Develop Schedule | T | Agile release planning
213 | Planning | Project Schedule Management | Develop Schedule | O | Schedule baseline
214 | Planning | Project Schedule Management | Develop Schedule | O | Project schedule
215 | Planning | Project Schedule Management | Develop Schedule | O | Schedule data
216 | Planning | Project Schedule Management | Develop Schedule | O | Project calendars
217 | Planning | Project Schedule Management | Develop Schedule | O | Change requests
218 | Planning | Project Schedule Management | Develop Schedule | O | Project management plan updates | Schedule management plan; Cost baseline
219 | Planning | Project Schedule Management | Develop Schedule | O | Project documents updates | Activity attributes; Assumption log; Duration of estimates; Lessons learned register; Resource requirements; Risk register
220 | Monitoring & Controlling | Project Schedule Management | Control Schedule | I | Project management plan | Schedule management plan; Schedule baseline; Scope baseline; Performance measurement baseline
221 | Monitoring & Controlling | Project Schedule Management | Control Schedule | I | Project documents | Lessons learned register; Project calendars; Project schedule; Resource calendars; Schedule data
222 | Monitoring & Controlling | Project Schedule Management | Control Schedule | I | Work performance data
223 | Monitoring & Controlling | Project Schedule Management | Control Schedule | I | Organizational process assets
224 | Monitoring & Controlling | Project Schedule Management | Control Schedule | T | Data analysis | Earned value analysis; Iteration burndown chart; Performance reviews; Trend analysis; Variance analysis; What-if scenario analysis
225 | Monitoring & Controlling | Project Schedule Management | Control Schedule | T | Critical path method
226 | Monitoring & Controlling | Project Schedule Management | Control Schedule | T | Project Management Information System (PMIS)
227 | Monitoring & Controlling | Project Schedule Management | Control Schedule | T | Resource optimization
228 | Monitoring & Controlling | Project Schedule Management | Control Schedule | T | Leads and Lags
229 | Monitoring & Controlling | Project Schedule Management | Control Schedule | T | Schedule compression
230 | Monitoring & Controlling | Project Schedule Management | Control Schedule | O | Work performance Information
231 | Monitoring & Controlling | Project Schedule Management | Control Schedule | O | Schedule Forecasts
232 | Monitoring & Controlling | Project Schedule Management | Control Schedule | O | Change requests
233 | Monitoring & Controlling | Project Schedule Management | Control Schedule | O | Project management plan updates | Schedule management plan; Schedule baseline; Cost baseline; Performance measurement baseline
234 | Monitoring & Controlling | Project Schedule Management | Control Schedule | O | Project documents updates | Assumption log; Basis of estimates; Lessons learned register; Project schedule; Resource calendars; Risk register; Schedule data
235 | Planning | Project Cost Management | Plan Cost Management | I | Project charter
236 | Planning | Project Cost Management | Plan Cost Management | I | Project management plan | Schedule management plan; Risk management plan
237 | Planning | Project Cost Management | Plan Cost Management | I | Enterprise environmental factors
238 | Planning | Project Cost Management | Plan Cost Management | I | Organizational process assets
239 | Planning | Project Cost Management | Plan Cost Management | T | Expert judgment
240 | Planning | Project Cost Management | Plan Cost Management | T | Data analysis | Alternatives analysis
241 | Planning | Project Cost Management | Plan Cost Management | T | Meetings
242 | Planning | Project Cost Management | Plan Cost Management | O | Cost management plan
243 | Planning | Project Cost Management | Estimate Costs | I | Project management plan | Cost management plan; Quality management plan; Scope baseline
244 | Planning | Project Cost Management | Estimate Costs | I | Project documents | Lessons learned register; Project schedule; Resource requirements; Risk register
245 | Planning | Project Cost Management | Estimate Costs | I | Enterprise environmental factors
246 | Planning | Project Cost Management | Estimate Costs | I | Organizational process assets
247 | Planning | Project Cost Management | Estimate Costs | T | Expert judgment
248 | Planning | Project Cost Management | Estimate Costs | T | Analogous estimating
249 | Planning | Project Cost Management | Estimate Costs | T | Parametric estimating
250 | Planning | Project Cost Management | Estimate Costs | T | Three-point estimating
251 | Planning | Project Cost Management | Estimate Costs | T | Bottom-up estimating
252 | Planning | Project Cost Management | Estimate Costs | T | Data analysis | Alternatives analysis; Reserve analysis; Cost of quality
253 | Planning | Project Cost Management | Estimate Costs | T | Project Management Information System (PMIS)
254 | Planning | Project Cost Management | Estimate Costs | T | Decision making | Voting
255 | Planning | Project Cost Management | Estimate Costs | O | Cost estimates
256 | Planning | Project Cost Management | Estimate Costs | O | Basis of estimates
257 | Planning | Project Cost Management | Estimate Costs | O | Project documents updates | Assumption log; Lessons learned register; Risk register
258 | Planning | Project Cost Management | Determine Budget | I | Project management plan | Cost management plan; Resource management plan; Scope baseline
259 | Planning | Project Cost Management | Determine Budget | I | Project documents | Basis of estimates; Cost estimates; Project schedule; Risk register
260 | Planning | Project Cost Management | Determine Budget | I | Business documents | Business case; Benefits management plan
261 | Planning | Project Cost Management | Determine Budget | I | Agreements
262 | Planning | Project Cost Management | Determine Budget | I | Enterprise environmental factors
263 | Planning | Project Cost Management | Determine Budget | I | Organizational process assets
264 | Planning | Project Cost Management | Determine Budget | T | Expert judgment
265 | Planning | Project Cost Management | Determine Budget | T | Cost aggregation
266 | Planning | Project Cost Management | Determine Budget | T | Data analysis | Reserve analysis
267 | Planning | Project Cost Management | Determine Budget | T | Historical information review
268 | Planning | Project Cost Management | Determine Budget | T | Funding limit reconciliation
269 | Planning | Project Cost Management | Determine Budget | T | Financing
270 | Planning | Project Cost Management | Determine Budget | O | Cost baseline
271 | Planning | Project Cost Management | Determine Budget | O | Project funding requirements
272 | Planning | Project Cost Management | Determine Budget | O | Project documents updates | Cost estimates; Project schedule; Risk register
273 | Monitoring & Controlling | Project Cost Management | Control Costs | I | Project management plan | Cost management plan; Cost baseline; Performance measurement baseline
274 | Monitoring & Controlling | Project Cost Management | Control Costs | I | Project documents | Lessons learned register
275 | Monitoring & Controlling | Project Cost Management | Control Costs | I | Project funding requirements
276 | Monitoring & Controlling | Project Cost Management | Control Costs | I | Work performance data
277 | Monitoring & Controlling | Project Cost Management | Control Costs | I | Organizational process assets
278 | Monitoring & Controlling | Project Cost Management | Control Costs | T | Expert judgment
279 | Monitoring & Controlling | Project Cost Management | Control Costs | T | Data analysis | Earned value analysis; Variance analysis; Trend analysis; Reserve analysis
280 | Monitoring & Controlling | Project Cost Management | Control Costs | T | To-complete performance index
281 | Monitoring & Controlling | Project Cost Management | Control Costs | T | Project Management Information System (PMIS)
282 | Monitoring & Controlling | Project Cost Management | Control Costs | O | Work performance Information
283 | Monitoring & Controlling | Project Cost Management | Control Costs | O | Cost forecasts
284 | Monitoring & Controlling | Project Cost Management | Control Costs | O | Change requests
285 | Monitoring & Controlling | Project Cost Management | Control Costs | O | Project management plan updates | Cost management plan; Cost baseline; Performance measurement baseline
286 | Monitoring & Controlling | Project Cost Management | Control Costs | O | Project documents updates | Assumption log; Basis of estimates; Lessons learned register; Risk register
287 | Planning | Project Quality Management | Plan Quality Management | I | Project charter
288 | Planning | Project Quality Management | Plan Quality Management | I | Project management plan | Requirements management plan; Rick management plan; Stakeholder engagement plan; Scope baseline
289 | Planning | Project Quality Management | Plan Quality Management | I | Project documents | Assumption log; Requirements documentation; Requirements traceability matrix; Risk register; Stakeholder register
290 | Planning | Project Quality Management | Plan Quality Management | I | Enterprise environmental factors
291 | Planning | Project Quality Management | Plan Quality Management | I | Organizational process assets
292 | Planning | Project Quality Management | Plan Quality Management | T | Expert judgment
293 | Planning | Project Quality Management | Plan Quality Management | T | Data gathering | Benchmarking; Brainstorming; Interviews
294 | Planning | Project Quality Management | Plan Quality Management | T | Data analysis | Cost-benefit analysis; Cost of quality
295 | Planning | Project Quality Management | Plan Quality Management | T | Decision making | Multi-criteria decision analysis
296 | Planning | Project Quality Management | Plan Quality Management | T | Data representation | Flowcharts; Logical data model; Matrix diagrams; Mind mapping
297 | Planning | Project Quality Management | Plan Quality Management | T | Test and inspection planning
298 | Planning | Project Quality Management | Plan Quality Management | T | Meetings
299 | Planning | Project Quality Management | Plan Quality Management | O | Quality management plan
300 | Planning | Project Quality Management | Plan Quality Management | O | Quality metrics
301 | Planning | Project Quality Management | Plan Quality Management | O | Project management plan updates | Risk management plan; Scope baseline
302 | Planning | Project Quality Management | Plan Quality Management | O | Project documents updates | Lessons learned register; Requirements traceability matrix; Risk register; Stakeholder register
303 | Executing | Project Quality Management | Manage Quality | I | Project management plan | Quality management plan
304 | Executing | Project Quality Management | Manage Quality | I | Project documents | Lessons learned register; Quality control measurements; Quality metrics; Risk report
305 | Executing | Project Quality Management | Manage Quality | I | Organizational process assets
306 | Executing | Project Quality Management | Manage Quality | T | Data gathering | Checklists
307 | Executing | Project Quality Management | Manage Quality | T | Data analysis | Alternatives analysis; Document analysis; Process analysis; Root cause analysis
308 | Executing | Project Quality Management | Manage Quality | T | Decision making | Multi-criteria decision analysis
309 | Executing | Project Quality Management | Manage Quality | T | Data representation | Affinity diagrams; Cause-and-effect diagrams; Flowcharts; Histograms; Matrix diagrams; Scatter diagrams
310 | Executing | Project Quality Management | Manage Quality | T | Audits
311 | Executing | Project Quality Management | Manage Quality | T | Design for X
312 | Executing | Project Quality Management | Manage Quality | T | Problem solving
313 | Executing | Project Quality Management | Manage Quality | T | Quality improvement methods
314 | Executing | Project Quality Management | Manage Quality | O | Quality reports
315 | Executing | Project Quality Management | Manage Quality | O | Test and evaluation documents
316 | Executing | Project Quality Management | Manage Quality | O | Change requests
317 | Executing | Project Quality Management | Manage Quality | O | Project management plan updates | Quality management plan; Scope baseline; Schedule baseline; Cost baseline
318 | Executing | Project Quality Management | Manage Quality | O | Project documents updates | Issue log; Lessons learned register; Risk register
319 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Project management plan | Quality management plan
320 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Project documents | Lessons learned register; Quality metrics; Test and evaluation documents
321 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Approved change requests
322 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Deliverables
323 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Work performance data
324 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Enterprise environmental factors
325 | Monitoring & Controlling | Project Quality Management | Control Quality | I | Organizational process assets
326 | Monitoring & Controlling | Project Quality Management | Control Quality | T | Data gathering | Checklists; Check sheets; Statistical sample; Questionnaires & surveys
327 | Monitoring & Controlling | Project Quality Management | Control Quality | T | Data analysis | Performance reviews; Root cause analysis
328 | Monitoring & Controlling | Project Quality Management | Control Quality | T | Inspection
329 | Monitoring & Controlling | Project Quality Management | Control Quality | T | Testing/product evaluation
330 | Monitoring & Controlling | Project Quality Management | Control Quality | T | Data representation | Cause-and-effect diagrams; Control charts; Histograms; Scatter diagrams
331 | Monitoring & Controlling | Project Quality Management | Control Quality | T | Meetings
332 | Monitoring & Controlling | Project Quality Management | Control Quality | O | Quality control measurements
333 | Monitoring & Controlling | Project Quality Management | Control Quality | O | Verified deliverables
334 | Monitoring & Controlling | Project Quality Management | Control Quality | O | Work performance Information
335 | Monitoring & Controlling | Project Quality Management | Control Quality | O | Change requests
336 | Monitoring & Controlling | Project Quality Management | Control Quality | O | Project management plan updates | Quality management plan
337 | Monitoring & Controlling | Project Quality Management | Control Quality | O | Project documents updates | Issue log; Lessons learned register; Risk register; Test and evaluation documents
338 | Planning | Project Resource Management | Plan Resource Management | I | Project charter
339 | Planning | Project Resource Management | Plan Resource Management | I | Project management plan | Quality management plan; Scope baseline
340 | Planning | Project Resource Management | Plan Resource Management | I | Project documents | Project schedule; Requirements documentation; Risk register; Stakeholder register
341 | Planning | Project Resource Management | Plan Resource Management | I | Enterprise environmental factors
342 | Planning | Project Resource Management | Plan Resource Management | I | Organizational process assets
343 | Planning | Project Resource Management | Plan Resource Management | T | Expert judgment
344 | Planning | Project Resource Management | Plan Resource Management | T | Data representation | Hierarchical charts; Responsibility assignment matrix; Text-oriented formats
345 | Planning | Project Resource Management | Plan Resource Management | T | Organizational theory
346 | Planning | Project Resource Management | Plan Resource Management | T | Meetings
347 | Planning | Project Resource Management | Plan Resource Management | O | Resource management plan
348 | Planning | Project Resource Management | Plan Resource Management | O | Team charter
349 | Planning | Project Resource Management | Plan Resource Management | O | Project documents updates | Assumption log; Risk register
350 | Planning | Project Resource Management | Estimate Activity Resources | I | Project management plan | Resource management plan; Scope baseline
351 | Planning | Project Resource Management | Estimate Activity Resources | I | Project Documents | Activity attributes; Activity list; Assumption log; Cost estimates; Resource calendars
352 | Planning | Project Resource Management | Estimate Activity Resources | I | Enterprise environmental factors
353 | Planning | Project Resource Management | Estimate Activity Resources | I | Organizational process assets
354 | Planning | Project Resource Management | Estimate Activity Resources | T | Expert judgment
355 | Planning | Project Resource Management | Estimate Activity Resources | T | Bottom-up estimating
356 | Planning | Project Resource Management | Estimate Activity Resources | T | Analogous estimating
357 | Planning | Project Resource Management | Estimate Activity Resources | T | Parametric estimating
358 | Planning | Project Resource Management | Estimate Activity Resources | T | Data analysis | Alternatives analysis
359 | Planning | Project Resource Management | Estimate Activity Resources | T | Project Management Information System (PMIS)
360 | Planning | Project Resource Management | Estimate Activity Resources | T | Meetings
361 | Planning | Project Resource Management | Estimate Activity Resources | O | Resource requirements
362 | Planning | Project Resource Management | Estimate Activity Resources | O | Basis of estimates
363 | Planning | Project Resource Management | Estimate Activity Resources | O | Resource breakdown structure
364 | Planning | Project Resource Management | Estimate Activity Resources | O | Project documents updates | Activity attributes; Assumption log; Lessons learned register
365 | Executing | Project Resource Management | Acquire Resources | I | Project management plan | Resource management plan; Procurement management plan; Cost baseline
366 | Executing | Project Resource Management | Acquire Resources | I | Project documents | Project Schedule; Resource calendars; Resource requirements; Stakeholder register
367 | Executing | Project Resource Management | Acquire Resources | I | Enterprise environmental factors
368 | Executing | Project Resource Management | Acquire Resources | I | Organizational process assets
369 | Executing | Project Resource Management | Acquire Resources | T | Decision making | Multi-criteria decision analysis
370 | Executing | Project Resource Management | Acquire Resources | T | Interpersonal & team skills | Negotiation
371 | Executing | Project Resource Management | Acquire Resources | T | Pre-assignment
372 | Executing | Project Resource Management | Acquire Resources | T | Virtual teams
373 | Executing | Project Resource Management | Acquire Resources | O | Physical resource assignments
374 | Executing | Project Resource Management | Acquire Resources | O | Project team assignments
375 | Executing | Project Resource Management | Acquire Resources | O | Resource calendars
376 | Executing | Project Resource Management | Acquire Resources | O | Change requests
377 | Executing | Project Resource Management | Acquire Resources | O | Project management plan updates | Resource management plan; Cost baseline
378 | Executing | Project Resource Management | Acquire Resources | O | Project documents updates | Lessons learned register; Project Schedule; Resource breakdown structure; Resource requirements; Risk register; Stakeholder register
379 | Executing | Project Resource Management | Acquire Resources | O | Enterprise environmental factors updates
380 | Executing | Project Resource Management | Acquire Resources | O | Organizational process assets updates
381 | Executing | Project Resource Management | Develop Team | I | Project management plan | Resource management plan
382 | Executing | Project Resource Management | Develop Team | I | Project documents | Lessons learned register; Project schedule; Project team assignments; Resource calendars; Team charter
383 | Executing | Project Resource Management | Develop Team | I | Enterprise environmental factors
384 | Executing | Project Resource Management | Develop Team | I | Organizational process assets
385 | Executing | Project Resource Management | Develop Team | T | Co-location
386 | Executing | Project Resource Management | Develop Team | T | Virtual teams
387 | Executing | Project Resource Management | Develop Team | T | Communication technology
388 | Executing | Project Resource Management | Develop Team | T | Interpersonal & team skills | Conflict management; Influencing; Motivation; Negotiation; Team building
389 | Executing | Project Resource Management | Develop Team | T | Recognition and rewards
390 | Executing | Project Resource Management | Develop Team | T | Training
391 | Executing | Project Resource Management | Develop Team | T | Individual and team assessments
392 | Executing | Project Resource Management | Develop Team | T | Meetings
393 | Executing | Project Resource Management | Develop Team | O | Team performance assessments
394 | Executing | Project Resource Management | Develop Team | O | Change requests
395 | Executing | Project Resource Management | Develop Team | O | Project management plan updates | Resource management plan
396 | Executing | Project Resource Management | Develop Team | O | Project documents updates | Lessons learned register; Project schedule; Project team assignments; Resource calendars; Team charter
397 | Executing | Project Resource Management | Develop Team | O | Enterprise environmental factors updates
398 | Executing | Project Resource Management | Develop Team | O | Organizational process assets updates
399 | Executing | Project Resource Management | Manage Team | I | Project management plan | Resource management plan
400 | Executing | Project Resource Management | Manage Team | I | Project documents | Issue log; Lessons learned register; Project team assignments; Team charter
401 | Executing | Project Resource Management | Manage Team | I | Work performance reports
402 | Executing | Project Resource Management | Manage Team | I | Team performance assessments
403 | Executing | Project Resource Management | Manage Team | I | Enterprise environmental factors
404 | Executing | Project Resource Management | Manage Team | I | Organizational process assets
405 | Executing | Project Resource Management | Manage Team | T | Interpersonal & team skills | Conflict management; Decision making; Emotional intelligence; Influencing; Leadership
406 | Executing | Project Resource Management | Manage Team | T | Project Management Information System (PMIS)
407 | Executing | Project Resource Management | Manage Team | O | Change requests
408 | Executing | Project Resource Management | Manage Team | O | Project management plan updates | Resource management plan; Schedule baseline; Cost baseline
409 | Executing | Project Resource Management | Manage Team | O | Project documents updates | Issue log; Lessons learned register; Project team assignments
410 | Executing | Project Resource Management | Manage Team | O | Enterprise environmental factors updates
411 | Monitoring & Controlling | Project Resource Management | Control Resources | I | Project management plan | Resource management plan
412 | Monitoring & Controlling | Project Resource Management | Control Resources | I | Project documents | Issue log; Lessons learned register; Physical resource assignments; Project schedule; Resource breakdown structure; Resource requirements; Risk register
413 | Monitoring & Controlling | Project Resource Management | Control Resources | I | Work performance data
414 | Monitoring & Controlling | Project Resource Management | Control Resources | I | Agreements
415 | Monitoring & Controlling | Project Resource Management | Control Resources | I | Organizational process assets
416 | Monitoring & Controlling | Project Resource Management | Control Resources | T | Data analysis | Alternatives analysis; Cost-benefit analysis; Performance reviews; Trend analysis
417 | Monitoring & Controlling | Project Resource Management | Control Resources | T | Problem solving
418 | Monitoring & Controlling | Project Resource Management | Control Resources | T | Interpersonal & team skills | Negotiation; Influencing
419 | Monitoring & Controlling | Project Resource Management | Control Resources | T | Project Management Information System (PMIS)
420 | Monitoring & Controlling | Project Resource Management | Control Resources | O | Work performance Information
421 | Monitoring & Controlling | Project Resource Management | Control Resources | O | Change requests
422 | Monitoring & Controlling | Project Resource Management | Control Resources | O | Project management plan updates | Resource management plan; Schedule baseline; Cost baseline
423 | Monitoring & Controlling | Project Resource Management | Control Resources | O | Project documents updates | Assumption log; Issue log; Lessons learned register; Physical resource assignments; Resource breakdown structure; Risk register
424 | Planning | Project Communications Management | Plan Communications Management | I | Project charter
425 | Planning | Project Communications Management | Plan Communications Management | I | Project management plan | Resource management plan; Stakeholder engagement plan
426 | Planning | Project Communications Management | Plan Communications Management | I | Project documents | Requirements documentation; Stakeholder register
427 | Planning | Project Communications Management | Plan Communications Management | I | Enterprise environmental factors
428 | Planning | Project Communications Management | Plan Communications Management | I | Organizational process assets
429 | Planning | Project Communications Management | Plan Communications Management | T | Expert judgment
430 | Planning | Project Communications Management | Plan Communications Management | T | Communications requirements analysis
431 | Planning | Project Communications Management | Plan Communications Management | T | Communication technology
432 | Planning | Project Communications Management | Plan Communications Management | T | Communication models
433 | Planning | Project Communications Management | Plan Communications Management | T | Communication methods
434 | Planning | Project Communications Management | Plan Communications Management | T | Interpersonal & team skills | Communication styles assessment; Political awareness; Cultural awareness
435 | Planning | Project Communications Management | Plan Communications Management | T | Data representation | Stakeholder engagement assessment matrix
436 | Planning | Project Communications Management | Plan Communications Management | T | Meetings
437 | Planning | Project Communications Management | Plan Communications Management | O | Communication management plan
438 | Planning | Project Communications Management | Plan Communications Management | O | Project management plan updates | Stakeholder engagement plan
439 | Planning | Project Communications Management | Plan Communications Management | O | Project documents updates | Project schedule; Stakeholder register
440 | Executing | Project Communications Management | Manage Communications | I | Project management plan | Resource management plan; Communications management plan; Stakeholder engagement plan
441 | Executing | Project Communications Management | Manage Communications | I | Project documents | Change log; Issue log; Lessons learned register; Quality reports; Risk report; Stakeholder register
442 | Executing | Project Communications Management | Manage Communications | I | Work performance reports
443 | Executing | Project Communications Management | Manage Communications | I | Enterprise environmental factors
444 | Executing | Project Communications Management | Manage Communications | I | Organizational process assets
445 | Executing | Project Communications Management | Manage Communications | T | Communication technology
446 | Executing | Project Communications Management | Manage Communications | T | Communication methods
447 | Executing | Project Communications Management | Manage Communications | T | Communication skills | Communication competence; Feedback; Nonverbal; Presentations
448 | Executing | Project Communications Management | Manage Communications | T | Project Management Information System (PMIS)
449 | Executing | Project Communications Management | Manage Communications | T | Project reporting
450 | Executing | Project Communications Management | Manage Communications | T | Interpersonal & team skills | Active listening; Conflict management; Cultural awareness; Meeting management; Networking; Political awareness
451 | Executing | Project Communications Management | Manage Communications | T | Meetings
452 | Executing | Project Communications Management | Manage Communications | O | Project communications
453 | Executing | Project Communications Management | Manage Communications | O | Project management plan updates | Communications management plan; Stakeholder engagement plan
454 | Executing | Project Communications Management | Manage Communications | O | Project documents updates | Issue log; Lessons learned register; Project schedule; Stakeholder register
455 | Executing | Project Communications Management | Manage Communications | O | Organizational process assets updates
456 | Monitoring & Controlling | Project Communications Management | Monitor Communications | I | Project management plan | Resource management plan; Communications management plan; Stakeholder engagement plan
457 | Monitoring & Controlling | Project Communications Management | Monitor Communications | I | Project documents | Issue log; Lessons learned register; Project communications
458 | Monitoring & Controlling | Project Communications Management | Monitor Communications | I | Work performance data
459 | Monitoring & Controlling | Project Communications Management | Monitor Communications | I | Enterprise environmental factors
460 | Monitoring & Controlling | Project Communications Management | Monitor Communications | I | Organizational process assets
461 | Monitoring & Controlling | Project Communications Management | Monitor Communications | T | Expert judgment
462 | Monitoring & Controlling | Project Communications Management | Monitor Communications | T | Project Management Information System (PMIS)
463 | Monitoring & Controlling | Project Communications Management | Monitor Communications | T | Data representation | Stakeholder engagement assessment matrix
464 | Monitoring & Controlling | Project Communications Management | Monitor Communications | T | Interpersonal & team skills | Observation/conversation
465 | Monitoring & Controlling | Project Communications Management | Monitor Communications | T | Meetings
466 | Monitoring & Controlling | Project Communications Management | Monitor Communications | O | Work performance information
467 | Monitoring & Controlling | Project Communications Management | Monitor Communications | O | Change requests
468 | Monitoring & Controlling | Project Communications Management | Monitor Communications | O | Project management plan updates | Communications management plan; Stakeholder engagement plan
469 | Monitoring & Controlling | Project Communications Management | Monitor Communications | O | Project documents updates | Issue log; Lessons learned register; Stakeholder register
470 | Planning | Project Risk Management | Plan Risk Management | I | Project charter
471 | Planning | Project Risk Management | Plan Risk Management | I | Project management plan | All components
472 | Planning | Project Risk Management | Plan Risk Management | I | Project documents | Stakeholder register
473 | Planning | Project Risk Management | Plan Risk Management | I | Enterprise environmental factors
474 | Planning | Project Risk Management | Plan Risk Management | I | Organizational process assets
475 | Planning | Project Risk Management | Plan Risk Management | T | Expert judgment
476 | Planning | Project Risk Management | Plan Risk Management | T | Data analysis | Stakeholder analysis
477 | Planning | Project Risk Management | Plan Risk Management | T | Meetings
478 | Planning | Project Risk Management | Plan Risk Management | O | Risk management plan
479 | Planning | Project Risk Management | Identify Risks | I | Project management plan | Requirements management plan; Schedule management plan; Cost management plan; Quality management plan; Resource management plan; Risk management plan; Scope baseline; Schedule baseline; Cost baseline
480 | Planning | Project Risk Management | Identify Risks | I | Project documents | Assumption log; Cost estimates; Duration of estimates; Issue log; Lessons learned register; Requirements documentation; Resource requirements; Stakeholder register
481 | Planning | Project Risk Management | Identify Risks | I | Agreements
482 | Planning | Project Risk Management | Identify Risks | I | Procurement documentation | Bid Documents; Procurement statement of work; Independent cost estimates; Source selection criteria
483 | Planning | Project Risk Management | Identify Risks | I | Enterprise environmental factors
484 | Planning | Project Risk Management | Identify Risks | I | Organizational process assets
485 | Planning | Project Risk Management | Identify Risks | T | Expert judgment
486 | Planning | Project Risk Management | Identify Risks | T | Data gathering | Brainstorming; Checklists; Interviews
487 | Planning | Project Risk Management | Identify Risks | T | Data analysis | Root cause analysis; Assumption and constraint analysis; SWOT analysis; Document analysis
488 | Planning | Project Risk Management | Identify Risks | T | Interpersonal & team skills | Facilitation
489 | Planning | Project Risk Management | Identify Risks | T | Prompt lists
490 | Planning | Project Risk Management | Identify Risks | T | Meetings
491 | Planning | Project Risk Management | Identify Risks | O | Risk register
492 | Planning | Project Risk Management | Identify Risks | O | Risk report
493 | Planning | Project Risk Management | Identify Risks | O | Project documents updates | Assumption log; Issue log; Lessons learned register
494 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | I | Project management plan | Risk management plan
495 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | I | Project documents | Assumption log; Risk register; Stakeholder register
496 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | I | Enterprise environmental factors
497 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | I | Organizational process assets
498 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Expert judgment
499 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Data gathering | Interviews
500 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Data analysis | Risk data quality assessment; Risk probability and impact assessment; assessment of other risk parameters
501 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Interpersonal & team skills | Facilitation
502 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Risk categorization
503 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Data representation | Probability and impact matrix; Hierarchical charts
504 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | T | Meetings
505 | Planning | Project Risk Management | Perform Qualitative Risk Analysis | O | Project documents updates | Assumption log; issue log; Risk register; Risk report
506 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | I | Project management plan | Risk management plan; Scope baseline; Schedule baseline; Cost baseline
507 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | I | Project documents | Assumption log; Basis of estimates; Cost estimates; Cost forecasts; Duration of estimates; Milestone list; Resource requirements; Risk register; Risk report; Schedule forecasts
508 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | I | Enterprise environmental factors
509 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | I | Organizational process assets
510 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | T | Expert judgment
511 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | T | Data gathering | Interviews
512 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | T | Interpersonal & team skills | Facilitation
513 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | T | Representations of uncertainty
514 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | T | Data analysis | Simulation; Sensitivity analysis; Decision tree analysis; Influence diagrams
515 | Planning | Project Risk Management | Perform Quantitative Risk Analysis | O | Project documents updates | Risk report
516 | Planning | Project Risk Management | Plan Risk Responses | I | Project management plan | Resource management plan; Risk management plan; Cost baseline
517 | Planning | Project Risk Management | Plan Risk Responses | I | Project documents | Lessons learned register; Project schedule; Project team assignments; Resource calendars; Risk register; Risk report; Stakeholder register
518 | Planning | Project Risk Management | Plan Risk Responses | I | Enterprise environmental factors
519 | Planning | Project Risk Management | Plan Risk Responses | I | Organizational process assets
520 | Planning | Project Risk Management | Plan Risk Responses | T | Expert judgment
521 | Planning | Project Risk Management | Plan Risk Responses | T | Data gathering | Interviews
522 | Planning | Project Risk Management | Plan Risk Responses | T | Interpersonal & team skills | Facilitation
523 | Planning | Project Risk Management | Plan Risk Responses | T | Strategies and threats
524 | Planning | Project Risk Management | Plan Risk Responses | T | Strategies and opportunities
525 | Planning | Project Risk Management | Plan Risk Responses | T | Contingent response strategies
526 | Planning | Project Risk Management | Plan Risk Responses | T | Strategies for overall project risk
527 | Planning | Project Risk Management | Plan Risk Responses | T | Data analysis | Alternatives analysis; Cost-benefit analysis
528 | Planning | Project Risk Management | Plan Risk Responses | T | Decision making | Multi-criteria decision analysis
529 | Planning | Project Risk Management | Plan Risk Responses | O | Change requests
530 | Planning | Project Risk Management | Plan Risk Responses | O | Project management plan updates | Schedule management plan; Cost management plan; Quality management plan; Resource management plan; Procurement management plan; Scope baseline; Schedule baseline; Cost baseline
531 | Planning | Project Risk Management | Plan Risk Responses | O | Project documents updates | Assumption log; Cost forecasts; Lessons learned register; Project schedule; Project team assignments; Risk register; Risk report
532 | Executing | Project Risk Management | Implement Risk Responses | I | Project management plan | Risk management plan
533 | Executing | Project Risk Management | Implement Risk Responses | I | Project documents | Lessons learned register; Risk register; Risk report
534 | Executing | Project Risk Management | Implement Risk Responses | I | Organizational process assets
535 | Executing | Project Risk Management | Implement Risk Responses | T | Expert judgment
536 | Executing | Project Risk Management | Implement Risk Responses | T | Interpersonal & team skills | Influencing
537 | Executing | Project Risk Management | Implement Risk Responses | T | Project Management Information System (PMIS)
538 | Executing | Project Risk Management | Implement Risk Responses | O | Change requests
539 | Executing | Project Risk Management | Implement Risk Responses | O | Project documents updates | Issue log; Lessons learned register; Project team assignments; Risk register; Risk report
540 | Monitoring & Controlling | Project Risk Management | Monitor Risks | I | Project management plan | Risk management plan
541 | Monitoring & Controlling | Project Risk Management | Monitor Risks | I | Project documents | Issue log; Lessons learned register; Risk register; Risk report
542 | Monitoring & Controlling | Project Risk Management | Monitor Risks | I | Work performance data
543 | Monitoring & Controlling | Project Risk Management | Monitor Risks | I | Work performance reports
544 | Monitoring & Controlling | Project Risk Management | Monitor Risks | T | Data analysis | Technical performance analysis; Reserve analysis
545 | Monitoring & Controlling | Project Risk Management | Monitor Risks | T | Audits
546 | Monitoring & Controlling | Project Risk Management | Monitor Risks | T | Meetings
547 | Monitoring & Controlling | Project Risk Management | Monitor Risks | O | Work performance information
548 | Monitoring & Controlling | Project Risk Management | Monitor Risks | O | Change requests
549 | Monitoring & Controlling | Project Risk Management | Monitor Risks | O | Project management plan updates | Any component
550 | Monitoring & Controlling | Project Risk Management | Monitor Risks | O | Project documents updates | Assumption log; Issue log; Lessons learned register; Risk register; Risk report
551 | Monitoring & Controlling | Project Risk Management | Monitor Risks | O | Organizational process assets updates
552 | Planning | Project Procurement Management | Plan Procurement Management | I | Project charter
553 | Planning | Project Procurement Management | Plan Procurement Management | I | Business documents | Business case; Benefits management plan
554 | Planning | Project Procurement Management | Plan Procurement Management | I | Project management plan | Scope management plan; Quality management plan; Resource management plan; Scope baseline
555 | Planning | Project Procurement Management | Plan Procurement Management | I | Project documents | Milestone list; Project team assignments; Requirements documentation; Requirements traceability matrix; Resource requirements; Risk register; Stakeholder register
556 | Planning | Project Procurement Management | Plan Procurement Management | I | Enterprise environmental factors
557 | Planning | Project Procurement Management | Plan Procurement Management | I | Organizational process assets
558 | Planning | Project Procurement Management | Plan Procurement Management | T | Expert judgment
559 | Planning | Project Procurement Management | Plan Procurement Management | T | Data gathering | Market research
560 | Planning | Project Procurement Management | Plan Procurement Management | T | Data analysis | Make-or-buy analysis
561 | Planning | Project Procurement Management | Plan Procurement Management | T | Source selection analysis
562 | Planning | Project Procurement Management | Plan Procurement Management | T | Meetings
563 | Planning | Project Procurement Management | Plan Procurement Management | O | Procurement management plan
564 | Planning | Project Procurement Management | Plan Procurement Management | O | Procurement strategy
565 | Planning | Project Procurement Management | Plan Procurement Management | O | Bid documents
566 | Planning | Project Procurement Management | Plan Procurement Management | O | Procurement statement of work
567 | Planning | Project Procurement Management | Plan Procurement Management | O | Source selection criteria
568 | Planning | Project Procurement Management | Plan Procurement Management | O | Make-or-buy decisions
569 | Planning | Project Procurement Management | Plan Procurement Management | O | Independent cost estimates
570 | Planning | Project Procurement Management | Plan Procurement Management | O | Change requests
571 | Planning | Project Procurement Management | Plan Procurement Management | O | Project documents updates | Lessons learned register; Milestone list; Requirements documentation; Requirements traceability matrix; Risk register; Stakeholder register
572 | Planning | Project Procurement Management | Plan Procurement Management | O | Organizational process assets updates
573 | Executing | Project Procurement Management | Conduct Procurements | I | Project management plan | Scope management plan; Communications management plan; Risk management plan; Procurement management plan; Configuration management plan; Cost baseline
574 | Executing | Project Procurement Management | Conduct Procurements | I | Project documents | Lessons learned register; Project schedule; Requirements documentation; Risk register; Stakeholder register
575 | Executing | Project Procurement Management | Conduct Procurements | I | Procurement documentation | Bid Documents; Procurement statement of work; Independent cost estimates; Source selection criteria
576 | Executing | Project Procurement Management | Conduct Procurements | I | Seller proposals
577 | Executing | Project Procurement Management | Conduct Procurements | I | Enterprise environmental factors
578 | Executing | Project Procurement Management | Conduct Procurements | I | Organizational process assets
579 | Executing | Project Procurement Management | Conduct Procurements | T | Expert judgment
580 | Executing | Project Procurement Management | Conduct Procurements | T | Advertising
581 | Executing | Project Procurement Management | Conduct Procurements | T | Bidder conferences
582 | Executing | Project Procurement Management | Conduct Procurements | T | Data analysis | Proposal evaluation
583 | Executing | Project Procurement Management | Conduct Procurements | T | Interpersonal & team skills | Negotiation
584 | Executing | Project Procurement Management | Conduct Procurements | O | Selected sellers
585 | Executing | Project Procurement Management | Conduct Procurements | O | Agreements
586 | Executing | Project Procurement Management | Conduct Procurements | O | Change requests
587 | Executing | Project Procurement Management | Conduct Procurements | O | Project management plan updates | Requirements management plan; Quality management plan; Risk management plan; Procurement management plan; Scope baseline; Schedule baseline; Cost baseline
588 | Executing | Project Procurement Management | Conduct Procurements | O | Project documents updates | Lessons learned register; Requirements documentation; requirements traceability matrix; Resource calendars; Risk register; Stakeholder register
589 | Executing | Project Procurement Management | Conduct Procurements | O | Organizational process assets updates
590 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Project management plan | Requirements management plan; Risk management plan; Procurement management plan; Change management plan; Schedule baseline
591 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Project documents | Assumption log; Lessons learned register; Milestone list; Quality reports; Requirements documentation; Requirements traceability matrix; Risk register; Stakeholder register
592 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Agreements
593 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Procurement documentation | Bid Documents; Procurement statement of work; Independent cost estimates; Source selection criteria
594 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Approved change requests
595 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Work performance data
596 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Enterprise environmental factors
597 | Monitoring & Controlling | Project Procurement Management | Control Procurements | I | Organizational process assets
598 | Monitoring & Controlling | Project Procurement Management | Control Procurements | T | Expert judgment
599 | Monitoring & Controlling | Project Procurement Management | Control Procurements | T | Claims administration
600 | Monitoring & Controlling | Project Procurement Management | Control Procurements | T | Data analysis | Performance reviews; Earned value analysis; Trend analysis
601 | Monitoring & Controlling | Project Procurement Management | Control Procurements | T | Inspection
602 | Monitoring & Controlling | Project Procurement Management | Control Procurements | T | Audits
603 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Closed procurements
604 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Work performance information
605 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Procurement documentation updates
606 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Change requests
607 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Project management plan updates | Risk management plan; Procurement management plan; Schedule baseline; Cost baseline
608 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Project documents updates | Lessons learned register; Resource requirements; Requirements traceability matrix; Risk register; Stakeholder register
609 | Monitoring & Controlling | Project Procurement Management | Control Procurements | O | Organizational process assets updates
610 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Project charter
611 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Business documents | Business case; Benefits management plan
612 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Project management plan | Communications management plan; Stakeholder engagement plan
613 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Project documents | Change log; Issue log; Requirements documentation
614 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Agreements
615 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Enterprise environmental factors
616 | Initiating | Project Stakeholder Management | Identify Stakeholders | I | Organizational process assets
617 | Initiating | Project Stakeholder Management | Identify Stakeholders | T | Expert judgment
618 | Initiating | Project Stakeholder Management | Identify Stakeholders | T | Data gathering | Questionnaires & surveys; Brainstorming
619 | Initiating | Project Stakeholder Management | Identify Stakeholders | T | Data analysis | Stakeholder analysis; Document analysis
620 | Initiating | Project Stakeholder Management | Identify Stakeholders | T | Data representation | Stakeholder mapping/representation
621 | Initiating | Project Stakeholder Management | Identify Stakeholders | T | Meetings
622 | Initiating | Project Stakeholder Management | Identify Stakeholders | O | Stakeholder register
623 | Initiating | Project Stakeholder Management | Identify Stakeholders | O | Change requests
624 | Initiating | Project Stakeholder Management | Identify Stakeholders | O | Project management plan updates | Requirements management plan; Communications management plan; Risk management plan; Stakeholder engagement plan
625 | Initiating | Project Stakeholder Management | Identify Stakeholders | O | Project documents updates | Assumption log; Issue log; Risk register
626 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | I | Project charter
627 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | I | Project management plan | Resource management plan; Communications management plan; Risk management plan
628 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | I | Project documents | Assumption log; Change log; Issue log; Project schedule; Risk register; Stakeholder register
629 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | I | Agreements
630 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | I | Enterprise environmental factors
631 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | I | Organizational process assets
632 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | T | Expert judgment
633 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | T | Data gathering | Benchmarking
634 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | T | Data analysis | Assumption and constraint analysis; Root cause analysis
635 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | T | Decision making | Prioritization/ranking
636 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | T | Data representation | Mind mapping; Stakeholder engagement assessment matrix
637 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | T | Meetings
638 | Planning | Project Stakeholder Management | Plan Stakeholder Engagement | O | Stakeholder engagement plan
639 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | I | Project management plan | Communications management plan; Risk management plan; Stakeholder engagement plan; Change management plan
640 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | I | Project documents | Change log; Issue log; Lessons learned register
641 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | I | Enterprise environmental factors
642 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | I | Organizational process assets
643 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | T | Expert judgment
644 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | T | Communication skills | Feedback
645 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | T | Interpersonal & team skills | Conflict management; Cultural awareness; Negotiation; Observation/conversation; Political awareness
646 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | T | Ground rules
647 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | T | Meetings
648 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | O | Change requests
649 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | O | Project management plan updates | Communications management plan; Stakeholder engagement plan
650 | Executing | Project Stakeholder Management | Manage Stakeholder Engagement | O | Project documents updates | Change log; Issue log; Lessons learned register; Stakeholder register
651 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | I | Project management plan | Resource management plan; Communications management plan; Stakeholder engagement plan
652 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | I | Project documents | Issue log; Lessons learned register; Project communications; Risk register; Stakeholder register
653 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | I | work performance data
654 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | I | Enterprise environmental factors
655 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | I | Organizational process assets
656 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | T | Data analysis | Alternatives analysis; Root cause analysis; Stakeholder analysis
657 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | T | Decision making | Multi-criteria decision analysis; Voting
658 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | T | Data representation | Stakeholder engagement assessment matrix
659 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | T | Communication skills | Feedback; Presentations
660 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | T | Interpersonal & team skills | Active listening; Cultural awareness; Leadership; Networking; Political awareness
661 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | T | Meetings
662 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | O | Work performance information
663 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | O | Change requests
664 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | O | Project management plan updates | Resource management plan; Communications management plan; Stakeholder engagement plan
665 | Monitoring & Controlling | Project Stakeholder Management | Monitor Stakeholder Engagement | O | Project documents updates | Issue log; Lessons learned register; Risk register; Stakeholder register

## ITO Desc
Name | Type Desc | Link | Parent | Notes | Description
Addition Project management plan | General |  | Project management plan |  | Additional component of project management plan (PMBOK 88)
Process | General |  |  |  | A management process is a set of interrelated actions and activities performed to achieve a pre-specified product, result, or service.
Inputs | General | I |  |  | Can be a document, a product, a service, or a result. A process will produce one or more primary outputs and may produce some ancillary outputs.
Outputs | General | O |  |  | Can be an output from another process, or things such as documents, company policies, and templates created outside of the project management processes.
Tools & Techniques | General | T |  |  | A specific, tangible item such as a template or software program, used in performing an activity to produce a product or result, or a defined systematic procedure to produce one or more outputs, which may also use one or more tools.
Process Group | General |  |  |  | A grouping of processes that will often operate at the same time or have similar inputs and outputs.
Initiating | Process Group |  |  |  | A set of processes that are utilized to define a new project or phase of an existing project by obtaining authorization to start the project
Planning | Process Group |  |  |  | A set of processes required to plan all aspects of the project.
Executing | Process Group |  |  |  | A set of processes where most of the actual work is performed and most of the resources are used. (IE the application is developed, a bridge is built)
Monitoring & Controlling | Process Group |  |  |  | A set of processes where the project is monitored for how it is progressing, and performance reports are provided on this progress. Projects are brought back into alignment through corrective actions where necessary.
Closing | Process Group |  |  |  | A set of processes where the project or phase is formally closed. All signoffs are obtained, historical records are transferred to the organization’s knowledgebase, and the project is handed off to the customer.
Knowledge Area | General |  |  |  | A group of processes that have similar characteristics and knowledge requirements.
Project Integration Management | Knowledge Area |  |  |  | This Knowledge area is about coordinating and unifying all the process from all the other knowledge areas together.
Project Scope Management | Knowledge Area |  |  |  | This Knowledge area is about providing the customer what they want. It provides no more, or less than the customer requirements. It involves managing both product scope and project scope. Controlling what is and what is not included in the project, while obtaining customer acceptance are also part of this area.
Project Schedule Management | Knowledge Area |  |  |  | This knowledge area is about defining the activities and schedule to deliver project work while also controlling the schedule.
Project Cost Management | Knowledge Area |  |  |  | This knowledge area is about estimating costs, determining the budget, and controlling the costs thereby allowing the project to be completed within the approved budget.
Project Quality Management | Knowledge Area |  |  |  | This knowledge area is about determining the quality policies, objective, and responsibilities to allow the project to satisfy the needs and function for which it is intended. It also deals with continuous improvement and controlling of the quality process.
Project Resource Management | Knowledge Area |  |  |  | This knowledge area is about determining the how you will manage, acquire, develop, and release the resources you need. Then execute the process of acquiring, developing, and managing these resources, while controlling the resources to ensure they are available and measure performance while taking corrective action when necessary.
Project Communications Management | Knowledge Area |  |  |  | This knowledge area is about understanding the communication needs for the project by determining how, what information, and when to dispense that information to meet the needs of the project. We then need to determine who is responsible for the communications and monitor the process to ensure that this is performed.
Project Risk Management | Knowledge Area |  |  |  | This knowledge area is about planning, identifying, analyzing, planning responses to both positive and negative risks. Then we need to implement the responses while monitoring the results.
Project Procurement Management | Knowledge Area |  |  |  | This knowledge area is about purchasing goods and services from outside the project. This includes planning, conducting, and controlling the contracts or purchase orders made by authorized project team members.
Project Stakeholder Management | Knowledge Area |  |  |  | This knowledge area is about identifying people, groups, or organizations that could impact, or be impacted by the project. Then analyze and plan how we will address and manage their needs while effectively managing a monitoring their engagement to the project.
Develop Project Charter | Process |  |  | Performed once or at predefined points. | Develops the document that formally authorizes the existence of the project, while providing the project manager the authority to run the project.
Develop Project Management Plan | Process |  |  | Performed once or at predefined points. | Defines, prepares, and consolidates all planning components into an integrated plan.
Direct and Manage Project Work | Process
Manage Project Knowledge | Process
Monitor and Control Project Work | Process
Perform Integrated Change Control | Process
Close Project or Phase | Process
Plan Scope Management | Process
Collect Requirements | Process
Define Scope | Process
Create WBS | Process
Validate Scope | Process
Control Scope | Process
Plan Schedule Management | Process
Define Activities | Process
Sequence Activities | Process
Estimate Activity Durations | Process
Develop Schedule | Process
Control Schedule | Process
Plan Cost Management | Process
Estimate Costs | Process
Determine Budget | Process
Control Costs | Process
Plan Quality Management | Process
Manage Quality | Process
Control Quality | Process
Plan Resource Management | Process
Estimate Activity Resources | Process
Acquire Resources | Process
Develop Team | Process
Manage Team | Process
Control Resources | Process
Plan Communications Management | Process
Manage Communications | Process
Monitor Communications | Process
Plan Risk Management | Process
Identify Risks | Process
Perform Qualitative Risk Analysis | Process
Perform Quantitative Risk Analysis | Process
Plan Risk Responses | Process
Implement Risk Responses | Process
Monitor Risks | Process
Plan Procurement Management | Process
Conduct Procurements | Process
Control Procurements | Process
Identify Stakeholders | Process
Plan Stakeholder Engagement | Process
Manage Stakeholder Engagement | Process
Monitor Stakeholder Engagement | Process
Agreements | Input/Output | IO |  |  | Documentation of mutual obligations. Usually this is between the seller to provide products, service, or results and the buyer. Always remember, unless otherwise stated, you are the buyer.
Business documents | Input/Output | IO |  |  | Two key business documents, maintained at the program level, that are relevant to project management. They can be developed with input from the Project manager but are primarily developed outside of the project. Documents include: Business case and Benefits management plan
Enterprise environmental factors | Input | I |  |  | Factors that are both internal and external to the organization tha influence the project's success.
Organizational process assets | Input | I |  |  | Assets that are internal to the organzation and are comprised two primary area: Processes, policies and procedures; Organizational knowledge databases
Expert judgment | Tool&Technique | T |  |  | Judgment based on expertise in a particular application area, knowledge area, discipline. Basically, put it to the team, or the subject matter expert (SME).
Data gathering
Interpersonal & team skills | Tool&Technique | T |  |  | Group of interpersonal and team skills that allow a Project manager to interact with stakeholders on a professional level.
Meetings | Tool&Technique | T |  |  | On projects meetings can be: Information exchange, Brainstorming, Decision making
Project charter |  |  |  |  | Document issued by the project sponsor that formally authorizes the existence of the project and provide the project manager the authority to run the project.
Assumption log | Input/Output | IO | Project Document |  | Document that records all assumptions and constraints throughout the project life cycle
Outputs from other processes
Project management plan updates
Project management plan
Project documents
Approved change requests
Project Management Information System (PMIS)
Deliverables
Work Performance Data
Issue Log
Change requests
Project documents updates
Organizational process assets updates
Knowledge management
Information management
Lessons learned Register
Work performance Information
Data analysis
Decision making | Tool&Technique | T |  |  | Group of techniques that involve working with others to reach a decision.
Work performance Reports
Change control tools
Accepted deliverables
Procurement documentation
Final product, service, or result transition
Final report
Scope management plan
Requirements management plan
Data representation
Context diagram
Prototypes
Requirements documentation
Requirements traceability matrix
Product analysis
Project scope statement
Decomposition
Scope baseline
Verified deliverables
Inspection
Schedule management plan
Rolling wave planning
Activity list
Activity attributes
Milestone list
Project management plan updates
Precedence diagramming method
Dependency determination and integration
Leads and lags
Project schedule network diagrams
Analogous estimating
Parametric estimating
Three-point estimating
Bottom-up estimating
Duration of estimates
Basis of estimates
Schedule network analysis
Critical path method
Resource optimization
Schedule compression
Agile release planning
Schedule baseline
Project schedule
Schedule data
Project calendars
Schedule Forecasts
Cost management plan
Cost estimates
Cost aggregation
Historical information review
Funding limit reconciliation
Financing
Cost baseline
Project funding requirements
To-complete performance index
Cost forecasts
Test and inspection planning
Quality management plan
Quality metrics
Audits
Design for X
Problem solving
Quality improvement methods
Quality reports
Test and evaluation documents
Testing/product evaluation
Quality control measurements
Organizational theory
Resource management plan
Team charter
Resource requirements
Resource breakdown structure
Pre-assignment
Virtual teams
Physical resource assignments
Project team assignments
Resource calendars
Enterprise environmental factors updates
Co-location
Communication technology
Recognition and rewards
Training
Individual and team assessments
Team performance assessments
Communications requirements analysis
Communication models
Communication methods
Communication management plan
Communication skills
Project reporting
Project communications
Risk management plan
Prompt lists
Risk register
Risk report
Risk categorization
Representations of uncertainty
Strategies and threats
Strategies and opportunities
Contingent response strategies
Strategies for overall project risk
Source selection analysis
Procurement management plan
Procurement strategy
Bid documents
Procurement statement of work
Source selection criteria
Make-or-buy decisions
Independent cost estimates
Seller proposals
Advertising
Bidder conferences
Selected sellers
Procurement documentation
Claims administration
Closed procurements
Procurement documentation updates
Stakeholder register
Stakeholder engagement plan
Ground rules
Business case | Input | I | Business documents |  | Document that clearly identifies the reasoning to justify the project and aligns the project objectives to business needs. The project sponsor is generally accountable for developing and maintaining this document. The project manager is responsible for providing input to this document.
Brainstorming | Tool&Technique | T | Data gathering |  | Data gathering technique led by a facilitator and conducted in a group setting to identify a list of ideas in a short period of time.
Focus groups | Tool&Technique | T | Data gathering |  | Data gathering technique bringing together a group of stakeholders and subject matter experts. A trained moderator guides the group through interactive discussions meant to be more conversational than one-sided.
Interviews | Tool&Technique | T | Data gathering |  | Data gathering technique that involves talking to stakeholders directly. Often conducted on an individual basis but may include multiple interviewees and interviewers. Useful in obtaining confidential information
Conflict management | Tool&Technique | T | Interpersonal & team skills |  | Ability to resolve conflicts on the project. Often forcing is the least preferred method while confronting is the best. However, conflicts resolution techniques should be chosen on a case by case basis. Conflict resolution types include (withdraw [or avoiding], smoothing [or accommodating], compromising, forcing, confronting [or problem solving])
Facilitation | Tool&Technique | T | Interpersonal & team skills |  | Ability to effectively guide a group event to a successful decision, solution, or conclusion.
Meeting management | Tool&Technique | T | Interpersonal & team skills |  | Ability to ensure that meetings meet their intended objectives effectively and efficiently.
Checklists
Change management plan
Configuration management plan
Performance measurement baseline
Project life cycle | Input/Output | IO | Addition Project management plan |  | Stages or phases a project passes through from initation to closing
Development approach | Input/Output | IO | Addition Project management plan |  | Description of the approach taken to develop the project, including predictive, iterative (functionality is refined [think of a whole painting that is improved]), incremental (functionality added in small portions [think of painting where sections are completed before starting a new section]), agile, or a hybrid model.
Management reviews
Any component
Change log
Risk register
Active listening
Leadership
Networking
Political awareness
Alternatives analysis
Cost-benefit analysis
Earned value analysis
Root cause analysis
Trend analysis
Variance analysis
Voting
All components
Benefits management plan
Document analysis
Regression analysis
Requirements management plan
Stakeholder engagement plan
Questionnaires & surveys
Benchmarking
Autocratic decision making
Multi-criteria decision analysis
Affinity diagrams
Mind mapping
Nominal group technique
Observation/conversation
Project team assignments
Reserve analysis
What-if scenario analysis
Simulation
Iteration burndown chart
Performance reviews
Cost of quality
Rick management plan
Flowcharts
Logical data model
Matrix diagrams
Process analysis
Cause-and-effect diagrams
Histograms
Scatter diagrams
Check sheets
Statistical sample
Control charts
Hierarchical charts
Responsibility assignment matrix
Text-oriented formats
Negotiation
Influencing
Motivation
Team building
Emotional intelligence
Communication styles assessment
Cultural awareness
Stakeholder engagement assessment matrix
Communications management plan
Communication competence
Feedback
Nonverbal
Presentations
Project communications
Stakeholder analysis
Assumption and constraint analysis
SWOT analysis
Risk data quality assessment
Risk probability and impact assessment
assessment of other risk parameters
Probability and impact matrix
Sensitivity analysis
Decision tree analysis
Influence diagrams
Technical performance analysis
Market research
Make-or-buy analysis
Proposal evaluation
Communications management plan
Stakeholder mapping/representation
Prioritization/ranking
Bid Documents
Procurement statement of work
Independent cost estimates
Source selection criteria

## EEFOPA
Description | Type | Process
Government or industry standards | Enterprise environmental factors | Develop Project Charter
Legal and regulatory requirements | Enterprise environmental factors | Develop Project Charter
Marketplace conditions | Enterprise environmental factors | Develop Project Charter
Organizational culture and political climate | Enterprise environmental factors | Develop Project Charter
Organizational governance framework | Enterprise environmental factors | Develop Project Charter
Stakeholders’ expectations and risk thresholds | Enterprise environmental factors | Develop Project Charter
Organizational standard policies, processes, and procedures | Organizational process assets | Develop Project Charter
Portfolio, program, and project governance framework | Organizational process assets | Develop Project Charter
Monitoring and reporting methods | Organizational process assets | Develop Project Charter
Templates | Organizational process assets | Develop Project Charter
Historical information and lessons learned repository | Organizational process assets | Develop Project Charter